## Revision Log
Document Change Log
Date | Version | Author | Change Description
2015-03-02 | v1.0 | Erwin Ramos | Initial Version.
2105-03-06 | v1.01 | Erwin Ramos | Update Assumption section step number 2. Added the EXECUTE permission in step. Update the create table in the VCP_release1.01.zip adding the custom schema XXNBTY.
2015-03-17 | v1.02 | Erwin Ramos | Added step 1 & 2 in Assumptions secrion.
2015-03-23 | v1.03 | Erwin Ramos | Update the VCP_release1.01.zip to VCP_release1.03.zip

## Program Files (hidden)
Description | RICEFW OBJECT
| LF-10 SUPPLIES ON HAND | LF-11 SUPPLIES IN TRANSIT | LF-14 SUPPLIES WORK ORDER | LF-16 WIP COMPONENT DEMAND | LF-17 SALES ORDER
Custom Request Set for UNIX script transfomation and Legacy Collection
Request Set
Request Set Links
Request Group
Unix Main program for WORK ORDER SUPPLY
Unix Sub program for WORK ORDER SUPPLY

## Deployment Plan
Installation Procedure:
Assumptions:
The following pre-requistes below are available in the server before executing the deployment plan for VCP RICEF Object.
1. The /home/nbtydata directory must have a permission of READ, WRITE & EXECUTE.
2. This object NBTY DM Forecast Export to ASCP has been deployed in the server already.
3. The server must have $XXNBTY_TOP directory. This is environment variable that defines the top-level directory for a given Oracle Application/product.
To check the $XXNBTY_TOP directory execute the command below in the server.
cd $XXNBTY_TOP
pwd
4. In the $XXNBTY_TOP directory the following subdirectories must available in the server with READ, WRITE & EXECUTE permission.
cd $XXNBTY_TOP/bin
cd $XXNBTY_TOP/sql
cd $XXNBTY_TOP/admin/import
cd $XXNBTY_TOP/admin/sql
cd $XXNBTY_TOP/data/tmp
cd $XXNBTY_TOP/data/in/arch
5. The user must have Application Developer Responsibility.
1. Upload folders and program files in the server.
1.1 Copy zip file.
1.2 Save and extract the zip file in your local directory.
1.3 Login into WINSCP application.
1.4 Open 'VCP_release1' directory.
1.5 Drag and drop all ' The VCP_RICEFW folder' into /home/nbtydata directory of the server instance.
NOTE: Make sure that the Transfer Settings of WINSCP is Binary.
1.6 Open 'Unix Script and Control Files' > drag and drop all files into /u01/oracle/apps/apps_st/appl/xxnbty/12.0.0/bin.
NOTE: Make sure that the Transfer Settings of WINSCP is Binary.
1.7 Open 'Packages' > drag and drop all files into /u01/oracle/apps/apps_st/appl/xxnbty/12.0.0/admin/sql
NOTE: Make sure that the Transfer Settings of WINSCP is Binary.
1.8 Open 'SQL Files' > drag and drop all Create Table sql files into /u01/oracle/apps/apps_st/appl/xxnbty/12.0.0/sql
NOTE: Make sure that the Transfer Settings of WINSCP is Binary.
1.8 Open 'FND Files' > drag and drop all FND files into /u01/oracle/apps/apps_st/appl/xxnbty/12.0.0/admin/import
NOTE: Make sure that the Transfer Settings of WINSCP is Binary.
2. Execute the deployment script and grant command
2.1 Login into UNIX application.
2.2 Navigate to VCP_RICEFW directory.
COMMAND:
cd /home/nbtydata/VCP_RICEFW
2.3 Change permission of VCP_deployment_script.sh file.
COMMAND:
chmod 777 VCP_batch_deployment.sh
2.4 Execute the dos2unix command for VCP_deployment_script.sh file.
COMMAND:
dos2unix VCP_batch_deployment.sh
2.5 Execute unix script then enter username and password.
COMMAND:
./VCP_batch_deployment.sh
2.5 Execute Grant command.
2.5.1 OPEN SQL Developer
2.5.2. Connect to VCP server Environment using APPS user with GRANT Privilege.
2.5.3. Open the sql script for grant in the SQL Developer.
You may see the grant script in the VCP_release1 --> Grant command
GRANT script:
2.5.4. Click Run Script in the SQL Developer.
NOTE: The user must have GRANT Privilege to execute the command.
3. Validate the program into frontend and database.
3.1 Login into oracle application
3.2 Click on System Administrator > Concurrent > Program > Define
3.3 Click on F11 to search the following program below.
XXNBTY Customer EXT for Demantra program
XXNBTY Item Description
XXNBTY Past Due Forecast Spreading
XXNBTY VCP Process Error Log
XXNBTY VCP Send Email Log
XXNBTY In Transit Supplies
XXNBTY Item Cost Merge Files
XXNBTY On Hand Supplies
XXNBTY Safety Stocks Generate Error Report
XXNBTY Safety Stocks Generate Report
XXNBTY Safety Stocks Load Program
XXNBTY Safety Stocks Validate Program
XXNBTY Sales Order
XXNBTY WIP Component Demand
XXNBTY Work Order Supplies
3.4 On the same responsibility go to > Application > Validation > Set
Search for the following Value sets below:
XXNBTY_MSC_REPROCESS
XXNBTY_ALLOW_SEND
XXNBTY_RICEFW_VCP
XXNBTY_MSC_FORECAST_CALENDAR
XXNBTY_MSC_BUCKET_TYPE
3.5 On the same responsibility go to Lookups > Common
Search for the following Look ups below:
XXNBTY_MSC_SAFETY_STKS_ERR_EML
XXNBTY_MSC_SAFETY_STOCKS_EMAIL
XXNBTY_VCP_COLL_REP_ADD_LKP
3.6 Change responsibility to Advanced Chain Supply Planner > Other > Requests > Submit a New Request > Request Set > Ok > Check the request sets in the LOV.
Check the following programs:
XXNBTY Daily Planning Request Set – MRP
XXNBTY Planning Request Set - MPS AND MRP
XXNBTY Monthly Planning Request Set - MRP
XXNBTY Weekly Planning Request Set - MRP
XXNBTY Monthly Planning Request Set - MPS
XXNBTY Weekly Planning Request Set – MPS
XXNBTY MSC In Transit Supplies Request Set
XXNBTY MSC Item Cost Request Set
XXNBTY MSC On Hand Supplies Request Set
XXNBTY MSC Safety Stocks Request Set
XXNBTY MSC Sales Order Request Set
XXNBTY MSC WIP Component Demand Request Set
XXNBTY MSC Work Order Supplies Request Set
3.7 Change responsibility to Advanced Chain Supply Planner > Other > Requests > Submit a New Request > Single Request > Ok > Check the single request in the LOV.
Check the following programs:
3.8 Check tables and packages in the database.
Open sql developer > expand the tables and Packages. Check the following tables and packages:
TABLES:
xxnbty_msc_costs_st
xxnbty_msc_safety_stocks_st
xxnbty_msc_spread_denorms
PACKAGE:
MSC_CL_CLEANSE
XXNBTY_MSCEXT01_ITEM_DESC_PKG
XXNBTY_MSCEXT02_CUSTOMER_PKG
XXNBTY_MSCEXT03_SPREAD_EXT_PKG
XXNBTY_MSCEXT05_SAFETY_STK_PKG
XXNBTY_VCP_SEND_EMAIL_PKG